## Read Me
Global Communications Calendar — FIRST DRAFT
One shared place for every outbound communication across AMER, EMEA and APAC — webinars, emails, social, events, PR, in-app and customer notices — so every team knows what goes out, when, to whom, and whether it's ready.
Tabs
Comms Calendar | The master list. One row per communication. This is the only tab most people edit.
Month View | Calendar grid for any month, filterable by region. Read-only.
Week View | Rolling 26 weeks: volume per region & channel, plus red flags. Use it in the weekly sync.
Dashboard | Headline numbers, region × channel, readiness by region, next 6 months.
Audience Lists | Official segment & list names, owners, consent basis, suppressions.
Owners & RACI | Who's who, who does what, and the proposed meeting rhythm & rules.
Rules & Guardrails | Frequency cap, content-lock, at-risk window, channel lead times, blackout dates.
Change Log | Record of changes after content lock or anything that moves another team's dates.
Dropdowns | Values behind every dropdown. Edit here to add a team, owner, time zone, etc.
How to add a comm
1. Add a row | On Comms Calendar, fill the white cells. Minimum: ID, Region, Channel, Target Segment, Launch Date, Owner, Overall Status.
2. Pick the audience | Use segment / list names from Audience Lists so the frequency and clash checks can match them.
3. Ops involved? | If Marketing Ops needs to build, pull lists or send: set 'Ops Involved? = Yes', raise a ticket, add the ticket #.
4. Track readiness | Update Content Status, Assets Ready?, List Ready?, Ops Ready? as work progresses. Readiness updates itself.
5. Watch the flags | Fix anything red: Over cap, Clash, Blackout, At Risk, Overdue, or a red 'Brief Due By' date.
6. After launch | Set Overall Status = Launched. Never delete rows — use Cancelled so history is kept.
Colour key
White cell | Input — type or pick from the dropdown.
Grey cell | Automatic formula — don't type over it.
Yellow cell | Setting / filter you can change (Rules & Guardrails, Month View, Week View).
Blue text | Editable assumption (e.g. lead times).
Readiness colours | Green = Ready · Yellow = In Progress · Orange = At Risk (inside the at-risk window) · Red = Overdue (date passed, not ready) · Blue = Launched.
How Readiness works
Ready | Content Approved AND Assets Yes/N/A AND List Yes/N/A AND (Ops not involved OR Ops Ready = Yes).
At Risk | Not ready and launching within the at-risk window (default 7 days).
Overdue | Not ready and launch date has passed (and status isn't Launched).
What's Missing | Lists exactly what still blocks the comm — use it to chase the right person.
Before rolling out
Example data | The rows dated Oct–Dec 2026 are illustrative examples (incl. a deliberate clash, cap breach and blackout). Replace them with real plans.
To confirm together | Owner names & emails · APAC owner · frequency cap · lead times · content-lock rule · blackout dates per region · RACI split.
Sharing | Put the file on SharePoint/OneDrive or upload to Google Sheets so everyone edits the same copy. Restrict Rules & Dropdowns edits to the calendar owners.

## Comms Calendar
Global Communications Calendar — AMER · EMEA · APAC
One row per communication (webinar, email, social post, event, customer notice...). White cells = fill in · Grey cells = automatic, don't type over them · Hover a header for guidance. Example rows are illustrative — replace them with real plans.
IDENTIFY | [5 empty] | CONTENT |  |  |  | AUDIENCE & LISTS |  |  |  | TIMING | [5 empty] | OWNERSHIP |  |  |  | READINESS | [9 empty] | AUTO CHECKS | [5 empty] | NOTES |  |  | HELPERS
ID | Region | Country / Market | Channel | Audience Type | Campaign / Program | Title / Subject Line | Key Message | CTA / Landing Page | Language | Target Segment | Lists Included | Lists Excluded / Suppression | Est. Reach (#) | Launch Date | Launch Time (local) | Time Zone | Frequency / Cadence | Touch # in Sequence | Brief Due By | Owner | Owning Team | Approver | Collaborators / Keep Informed | Content Status | Assets Ready? | List Ready? | Ops Involved? | Ops Ticket # | Ops Ready? | Overall Status | Readiness | What's Missing | Days to Launch | Week Commencing | Month | Same-Week Touches | Frequency Flag | Date Clash | Blackout Flag | Dependencies / Notes | Last Updated | Updated By | Channel Group | _Key
AM-001 | AMER | US & Canada | Email - Webinar Invite / Reminder | Customer | Q4 Roadmap Webinar | You're invited: What's next on our Q4 roadmap | Preview Q4 releases and get answers live from Product. | Register - /webinars/q4-roadmap | EN | AMER Customers - Active | AMER Customers - Active; AMER Champions | Unsubscribed; Open support escalations | 4800 | 2026-10-13 | 10:00 | ET | Sequence (multi-touch) | 1 of 3 | 2026-09-29 | Head of Mkt AMER | Digital | Head of Marketing (Global) | CS leadership; AMER Sales | Approved | Yes | Yes | Yes | OPS-1042 | Yes | Scheduled | Ready |  | 5 | 2026-10-12 | 2026-10-01 | 3 | Over cap | Clash |  | Depends on webinar landing page (Digital). | 2026-10-08 | Draft (example) | Email | 46308¦AMER
AM-002 | AMER | US & Canada | Email - Customer Notice | Customer | Platform Update | Important: upcoming maintenance window | Planned maintenance on 24 Oct, 2-4am ET. No action needed. | Status page | EN | AMER Customers - Active | AMER Customers - Active; AMER Admin Contacts | Unsubscribed (service msg - legal check) | 5200 | 2026-10-13 | 14:00 | ET | One-off |  | 2026-09-22 | Customer Success | Customer Success | Head of Mkt AMER | Support; Product | In review | Yes | No | Yes | OPS-1051 | No | In production | At Risk | Content approval, List, Ops | 5 | 2026-10-12 | 2026-10-01 | 3 | Over cap | Clash |  | EXAMPLE CLASH: same segment, same day as AM-001 - move one of them. | 2026-10-08 | Draft (example) | Email | 46308¦AMER
AM-003 | AMER | US & Canada | Email - Webinar Invite / Reminder | Customer | Q4 Roadmap Webinar | Reminder: Q4 roadmap webinar is next week | Last chance to save your seat. | Register - /webinars/q4-roadmap | EN | AMER Customers - Active | AMER Customers - Active; AMER Champions | Already registered; Unsubscribed | 4500 | 2026-10-15 | 10:00 | ET | Sequence (multi-touch) | 2 of 3 | 2026-10-01 | Head of Mkt AMER | Digital | Head of Marketing (Global) |  | Approved | Yes | Yes | Yes | OPS-1042 | Yes | Scheduled | Ready |  | 7 | 2026-10-12 | 2026-10-01 | 3 | Over cap |  |  | EXAMPLE: 3rd touch to this segment this week -> Over cap. | 2026-10-08 | Draft (example) | Email | 46310¦AMER
AM-004 | AMER | US & Canada | Webinar | Customer | Q4 Roadmap Webinar | Q4 Product Roadmap - Live Webinar | Live roadmap walkthrough + Q&A with Product leaders. | /webinars/q4-roadmap | EN | AMER Customers - Active | Registrants |  | 600 | 2026-10-22 | 11:00 | ET | One-off |  | 2026-09-10 | Head of Mkt AMER | Field Marketing | Head of Marketing (Global) | Product (speakers); AMER Sales | Approved | Yes | Yes | Yes | OPS-1040 | Yes | Scheduled | Ready |  | 14 | 2026-10-19 | 2026-10-01 | 1 | OK |  |  | Speakers confirmed. Dry run 20 Oct. | 2026-10-08 | Draft (example) | Webinar | 46317¦AMER
EM-001 | EMEA | UK & I, DACH, France | Email - Webinar Invite / Reminder | Customer + Prospect | Q4 Roadmap Webinar | Join us: Q4 roadmap live (EN/DE/FR) | Same story as AMER, localised for EMEA. | Register - /webinars/q4-roadmap-emea | Multi | EMEA Customers + Engaged Prospects | EMEA Customers - Active; EMEA Prospects - Engaged 90d | No GDPR consent; Unsubscribed | 9100 | 2026-10-14 | 09:00 | CET | Sequence (multi-touch) | 1 of 3 | 2026-09-30 | Head of Mkt EMEA | Digital | Head of Marketing (Global) | EMEA Sales; Localisation | In review | No | Yes | Yes | OPS-1047 | No | In production | At Risk | Content approval, Assets, Ops | 6 | 2026-10-12 | 2026-10-01 | 1 | OK |  |  | Waiting on DE/FR translations. | 2026-10-08 | Draft (example) | Email | 46309¦EMEA
EM-002 | EMEA | UK & I, DACH, France | Webinar | Customer + Prospect | Q4 Roadmap Webinar | Q4 Product Roadmap - EMEA session | Live roadmap + EMEA customer guest speaker. | /webinars/q4-roadmap-emea | EN | EMEA Customers + Engaged Prospects | Registrants |  | 750 | 2026-10-23 | 10:00 | CET | One-off |  | 2026-09-11 | Head of Mkt EMEA | Field Marketing | Head of Marketing (Global) | Product; EMEA Sales | Drafting | No | N/A | Yes |  | No | Planned | In Progress | Content approval, Assets, Ops | 15 | 2026-10-19 | 2026-10-01 | 1 | OK |  |  | Guest speaker TBC. | 2026-10-08 | Draft (example) | Webinar | 46318¦EMEA
EM-003 | EMEA | UK | Event - In-person | Customer | Customer Roundtables | Executive Customer Roundtable - London | Invite-only dinner with 20 strategic accounts. | RSVP | EN | EMEA Strategic Accounts | EMEA Strategic Accounts - Execs |  | 40 | 2026-11-12 | 18:30 | GMT/BST | One-off |  | 2026-09-17 | Field Marketing | Field Marketing | Head of Mkt EMEA | Account Execs; CS | Approved | Yes | Yes | No |  |  | Planned | Ready |  | 35 | 2026-11-09 | 2026-11-01 | 1 | OK |  |  | Venue booked. | 2026-10-08 | Draft (example) | Event | 46338¦EMEA
AP-001 | APAC | ANZ, SG, JP | Webinar | Customer + Prospect | Q4 Roadmap Webinar | Q4 Product Roadmap - APAC session | APAC-timed session of the roadmap webinar. | /webinars/q4-roadmap-apac | EN | APAC Customers + Engaged Prospects | APAC Customers - Active; APAC Prospects - Engaged 90d | Unsubscribed | 3000 | 2026-10-28 | 14:00 | SGT | One-off |  | 2026-09-16 | APAC Marketing Lead | Field Marketing | Head of Marketing (Global) | APAC Sales | Drafting | No | No | Yes |  |  | Planned | In Progress | Content approval, Assets, List, Ops | 20 | 2026-10-26 | 2026-10-01 | 1 | OK |  |  | Japanese subtitles for recording? | 2026-10-08 | Draft (example) | Webinar | 46323¦APAC
AP-002 | APAC | ANZ | Email - Campaign / Nurture | Prospect | APAC Nurture Q4 | 3 ways teams in ANZ cut reporting time | Value-led nurture, case study from a local customer. | Read the case study | EN | APAC Prospects - Engaged 90d | APAC Prospects - Engaged 90d | Customers; Open opportunities | 2100 | 2026-11-05 | 09:00 | AEST | Bi-weekly | 1 of 4 | 2026-10-22 | APAC Marketing Lead | Digital | Dean (Digital) | APAC SDRs | Not started | No | No | Yes |  |  | Planned | In Progress | Content approval, Assets, List, Ops | 28 | 2026-11-02 | 2026-11-01 | 1 | OK |  |  |  | 2026-10-08 | Draft (example) | Email | 46331¦APAC
GL-001 | Global | All | Email - Newsletter | Customer | Customer Newsletter | October customer newsletter | Product highlights, upcoming webinars by region, community spotlight. | Newsletter hub | EN | All Customers | All Customers - Active | Unsubscribed | 21000 | 2026-10-29 | 10:00 | ET | Monthly |  | 2026-10-15 | Dean (Digital) | Digital | Head of Marketing (Global) | Regional Heads (content inputs due 20 Oct) | Drafting | No | Yes | Yes | OPS-1055 | No | In production | In Progress | Content approval, Assets, Ops | 21 | 2026-10-26 | 2026-10-01 | 1 | OK |  |  | Each region sends 1-2 items by 20 Oct. | 2026-10-08 | Draft (example) | Email | 46324¦Global
GL-002 | Global | All | Social - LinkedIn | Customer + Prospect | Q4 Roadmap Webinar | Webinar promo post series | Promote all three regional sessions. | Regional registration pages | EN | Social followers | N/A | N/A |  | 2026-10-15 | 12:00 | ET | Weekly | 1 of 3 | 2026-10-12 | Dean (Digital) | Digital | Head of Marketing (Global) | Regional Heads | Approved | Yes | N/A | No |  |  | Scheduled | Ready |  | 7 | 2026-10-12 | 2026-10-01 | 1 | OK |  |  | Regional versions posted in local time zones. | 2026-10-08 | Draft (example) | Social | 46310¦Global
GL-003 | Global | All | Press Release / PR | Customer + Prospect | Winter Product Launch | Announcing our Winter release | Headline launch - embargo until 17 Nov 08:00 ET. | /winter-release | EN | Media + public | Press list |  |  | 2026-11-17 | 08:00 | ET | One-off |  | 2026-10-27 | Head of Marketing (Global) | Comms / PR | Head of Marketing (Global) | All regions; Sales; CS; Exec team | Drafting | No | N/A | No |  |  | Planned | In Progress | Content approval, Assets | 40 | 2026-11-16 | 2026-11-01 | 1 | OK |  |  | All launch comms on 17 Nov must wait for the embargo. | 2026-10-08 | Draft (example) | PR | 46343¦Global
GL-004 | Global | All | In-app / Product Message | Customer | Winter Product Launch | What's new: Winter release | In-product banner pointing to the release notes. | Release notes | Multi | All Customers | All active users |  | 60000 | 2026-11-17 | 09:00 | ET | One-off |  | 2026-11-03 | Product Marketing | Product Marketing | Head of Marketing (Global) | Product; Support | Not started | No | N/A | No |  |  | Planned | In Progress | Content approval, Assets | 40 | 2026-11-16 | 2026-11-01 | 1 | OK |  |  |  | 2026-10-08 | Draft (example) | In-app | 46343¦Global
AM-005 | AMER | US | Email - Campaign / Nurture | Prospect | Holiday Promo | Year-end offer for new teams | Annual plan incentive before 31 Dec. | Talk to sales | EN | AMER Prospects - Engaged 90d | AMER Prospects - Engaged 90d | Customers; Open opportunities | 6400 | 2026-11-27 | 10:00 | ET | One-off |  | 2026-11-13 | Head of Mkt AMER | Digital | Head of Marketing (Global) | AMER Sales | Not started | No | No | Yes |  |  | Planned | In Progress | Content approval, Assets, List, Ops | 50 | 2026-11-23 | 2026-11-01 | 1 | OK |  | Blackout | EXAMPLE: falls on a blackout date. | 2026-10-08 | Draft (example) | Email | 46353¦AMER
GL-005 | Global | All | Email - Newsletter | Customer | Customer Newsletter | Season's greetings & year in review | Thank-you note + 2026 highlights. | Year in review page | Multi | All Customers | All Customers - Active | Unsubscribed | 21000 | 2026-12-15 | 10:00 | ET | One-off |  | 2026-12-01 | Head of Marketing (Global) | Digital | Head of Marketing (Global) | All regions | Not started | No | Yes | Yes |  |  | Planned | In Progress | Content approval, Assets, Ops | 68 | 2026-12-14 | 2026-12-01 | 1 | OK |  |  |  | 2026-10-08 | Draft (example) | Email | 46371¦Global
Formulas:
Brief Due By = IF(OR([TIMING]="",[Channel]=""),"",WORKDAY([TIMING],-IFERROR(VLOOKUP([Channel],'Rules & Guardrails'!$A9:D24,3,0),10)))
Days to Launch = IF([TIMING]="","",[TIMING]-TODAY())
AUTO CHECKS = IF([TIMING]="","",[TIMING]-WEEKDAY([TIMING],3))
Month = IF([TIMING]="","",DATE(YEAR([TIMING]),MONTH([TIMING]),1))
Note on A4: Unique ID, e.g. AM-001 / EM-001 / AP-001 / GL-001.
Note on C4: Optional: e.g. US, UK & I, DACH, ANZ, Japan.
Note on D4: Pick from the list. Channels are managed on Rules & Guardrails.
Note on H4: One or two sentences: what do we want them to know / do?
Note on K4: Use the SAME segment name every time (see Audience Lists tab) — the frequency & clash checks match on it.
Note on L4: List names from the Audience Lists tab, separated by ;
Note on O4: Required — everything on the Month View, Week View and Dashboard keys off this date.
Note on P4: e.g. 10:00
Note on S4: e.g. 1 of 3
Note on T4: Auto: launch date minus the channel's brief lead time (business days).
Note on X4: Who else needs to know (Sales, CS, Product, Partners...).
Note on AB4: Yes = Marketing Ops builds / sends / pulls the list.
Note on AF4: Auto: Ready / In Progress / At Risk / Overdue (or the status if Launched, On hold, Cancelled).
Note on AG4: Auto: what still blocks this comm.
Note on AI4: Auto: Monday of the launch week.
Note on AK4: Auto: comms to the same segment, in the same region, in the same week.
Note on AL4: Auto: 'Over cap' when touches exceed the weekly max on Rules & Guardrails.
Note on AM4: Auto: 'Clash' when the same segment in the same region gets 2+ comms on the same day.
Note on AN4: Auto: 'Blackout' when the date is on the blackout list for this region (or Global).
Note on AR4: Helper used by Week View & Dashboard.
Note on AS4: Helper used by Month View.

## Month View
Month View
Month (any date in it): | 2026-10-01 |  | Region: | All |  | Total this month: 9
Change the yellow cells. Each day shows how many comms launch, the AM/EM/AP/GL split, and the first title. Cancelled items are excluded. Full detail lives on the Comms Calendar tab.
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04
0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11
0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18
0 | 2 | 1 | 2 | 0 | 0 | 0
| AM 2 · EM 0 · AP 0 · GL 0 | AM 0 · EM 1 · AP 0 · GL 0 | AM 1 · EM 0 · AP 0 · GL 1
| You're invited: What's next on our Q4 roadmap (+1 more) | Join us: Q4 roadmap live (EN/DE/FR) | Reminder: Q4 roadmap webinar is next week (+1 more)
2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25
0 | 0 | 0 | 1 | 1 | 0 | 0
|  |  | AM 1 · EM 0 · AP 0 · GL 0 | AM 0 · EM 1 · AP 0 · GL 0
|  |  | Q4 Product Roadmap - Live Webinar | Q4 Product Roadmap - EMEA session
2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01
0 | 0 | 1 | 1 | 0 | 0 | 0
|  | AM 0 · EM 0 · AP 1 · GL 0 | AM 0 · EM 0 · AP 0 · GL 1
|  | Q4 Product Roadmap - APAC session | October customer newsletter
2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08
0 | 0 | 0 | 1 | 0 | 0 | 0
AM 0 · EM 0 · AP 1 · GL 0
3 ways teams in ANZ cut reporting time
Legend: blue tint = 1-2 comms · orange tint = 3+ comms (check for overload) · yellow = today · grey = outside the month
Formulas:
Tuesday = [Monday]+1
Wednesday = [Tuesday]+1
Thursday = [Wednesday]+1
Friday = [Thursday]+1
Saturday = [Friday]+1
Sunday = [Saturday]+1

## Week View
Week View — rolling 26 weeks
First week (Monday): |  | 2026-10-05 | Defaults to the current week — overwrite with any date to look elsewhere.
Week Commencing | AMER | EMEA | APAC | Global | Total | Webinars | Emails | Social | Events | Customer-facing | Not Ready | Ops Involved | Over Cap | Clashes | Blackout
2026-10-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-12 | 3 | 1 | 0 | 1 | 5 | 0 | 4 | 1 | 0 | 5 | 2 | 4 | 3 | 2 | 0
2026-10-19 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 0
2026-10-26 | 0 | 0 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0
2026-11-02 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
2026-11-09 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2026-11-16 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
2026-11-23 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1
2026-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-12-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-12-14 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
2026-12-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-12-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027-01-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027-01-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027-01-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027-02-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027-02-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027-02-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027-03-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027-03-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027-03-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Red = needs attention. Orange total = busy week (6+ comms) — check audiences aren't being overloaded.
Formulas:
Week Commencing = [Week Commencing, row above]+7

## Dashboard
Alignment Dashboard
As of 08 Oct 2026 · excludes cancelled comms
Headline numbers
Comms planned (all dates) | 15
Launching next 7 days | 3
Launching next 30 days | 10
Ready rate (open comms) | 33.33%
At Risk + Overdue | 2
Waiting on Ops | 8
Frequency cap breaches | 3
Date clashes | 2
On blackout dates | 1
Comms by region × channel
Region | Webinar | Email | Social | Event | PR | In-app | Other | Total
AMER | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 5
EMEA | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 3
APAC | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2
Global | 0 | 2 | 1 | 0 | 1 | 1 | 0 | 5
Total | 3 | 8 | 1 | 1 | 1 | 1 | 0 | 15
Readiness by region
Region | Ready | In Progress | At Risk | Overdue | On hold | Launched | Waiting on Ops
AMER | 3 | 1 | 1 | 0 | 0 | 0 | 2
EMEA | 1 | 1 | 1 | 0 | 0 | 0 | 2
APAC | 0 | 2 | 0 | 0 | 0 | 0 | 2
Global | 1 | 4 | 0 | 0 | 0 | 0 | 2
Total | 5 | 8 | 2 | 0 | 0 | 0 | 8
Comms by region × month (next 6 months)
Region | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
AMER | 4 | 1 | 0 | 0 | 0 | 0
EMEA | 2 | 1 | 0 | 0 | 0 | 0
APAC | 1 | 1 | 0 | 0 | 0 | 0
Global | 2 | 2 | 1 | 0 | 0 | 0
Total | 9 | 5 | 1 | 0 | 0 | 0
Formulas:
Email = EDATE([Webinar],1)
Social = EDATE([Email],1)
Event = EDATE([Social],1)
PR = EDATE([Event],1)
In-app = EDATE([PR],1)

## Audience Lists
Audience & List Registry
Single source of truth for segment & list names. Use these exact names in the calendar so frequency and clash checks work. Marketing Ops owns list hygiene.
List / Segment Name | Region | Audience Type | Description / Criteria | Source System | Approx. Size | List Owner | Last Refreshed | Consent Basis | Standard Suppressions | Notes
AMER Customers - Active | AMER | Customer | Paying accounts, all active contacts | CRM | 5200 | Marketing Ops | 2026-10-01 | Customer relationship | Unsubscribed; Bounced
AMER Champions | AMER | Customer | Advocates / NPS 9-10 | CRM | 350 | Marketing Ops | 2026-09-15 | Customer relationship | Unsubscribed
AMER Prospects - Engaged 90d | AMER | Prospect | Opened/clicked/visited in last 90 days | MAP | 6400 | Marketing Ops | 2026-10-01 | Opt-in / legitimate interest | Customers; Open opps; Unsubscribed
EMEA Customers + Engaged Prospects | EMEA | Customer + Prospect | Combined segment for EMEA programs | CRM + MAP | 9100 | Marketing Ops | 2026-10-01 | GDPR: explicit consent required | No consent; Unsubscribed | Check consent per country
EMEA Strategic Accounts | EMEA | Customer | Top 50 accounts, exec contacts | CRM | 120 | Head of Mkt EMEA | 2026-09-30 | Customer relationship |  | Hand-curated with Sales
APAC Customers + Engaged Prospects | APAC | Customer + Prospect | Combined segment for APAC programs | CRM + MAP | 3000 | Marketing Ops | 2026-10-01 | Opt-in (check AU Spam Act, JP APPI) | Unsubscribed
APAC Prospects - Engaged 90d | APAC | Prospect | Engaged in last 90 days | MAP | 2100 | Marketing Ops | 2026-10-01 | Opt-in | Customers; Open opps
All Customers | Global | Customer | Every active customer contact worldwide | CRM | 21000 | Marketing Ops | 2026-10-01 | Customer relationship | Unsubscribed; Bounced

## Owners & RACI
Owners, RACI & Ways of Working
Who's who
Role | Name | Region / Scope | Email | Backup | Owns in this calendar
Head of Marketing (Global) |  | Global |  |  | Final say on the calendar, global launches, conflicts between regions
Head of Mkt AMER |  | AMER |  |  | AMER plan, webinars, campaigns; approves AMER rows
Head of Mkt EMEA |  | EMEA |  |  | EMEA plan, webinars, campaigns; approves EMEA rows
APAC Marketing Lead | TBC | APAC |  |  | APAC plan - owner to be confirmed
Dean (Digital) | Dean | Global - Digital |  |  | Email, newsletter, social, web; channel calendar & cadence
Field Marketing |  | All regions |  |  | Webinars & events logistics, speakers, registrations
Marketing Ops |  | Global |  |  | Lists, suppressions, builds, QA, sends, tracking; Ops tickets
Product Marketing |  | Global |  |  | Launch messaging, release notes, in-app
Customer Success |  | All regions |  |  | Customer notices; heads-up to CSMs before customer comms
RACI (R = Responsible · A = Accountable · C = Consulted · I = Informed)
Activity | Head of Mkt (Global) | Head of Mkt AMER | Head of Mkt EMEA | APAC Mkt Lead | Dean (Digital) | Field Marketing | Marketing Ops | Product Mktg | Customer Success
Calendar governance & final conflict resolution | A | R | R | R | R | C | C | I | I
Regional comms plan (AMER / EMEA / APAC) | A | R | R | R | C | C | C | C | I
Webinars (content, speakers, run of show) | A | R | R | R | C | R | C | C | I
Email campaigns & newsletter | A | C | C | C | R | I | R | C | I
Social media | A | C | C | C | R | I | I | C | I
Customer notices / customer-impacting comms | A | C | C | C | C | I | R | C | R
Audience definition & list selection | I | A | A | A | R | C | R | I | C
List pulls, suppressions, builds & QA | I | I | I | I | C | I | A/R | I | I
Send / launch execution | I | I | I | I | A | R | R | I | I
Approval of row before content lock | A | R | R | R | C | I | I | C | C
Product launch comms | A | C | C | C | R | C | R | R | I
Post-launch results & learnings | A | R | R | R | R | R | R | C | I
Proposed split — review and adjust together in the first sync.
Ways of working (proposed)
Ritual / Rule | A A A: When; R C R: Who; R C R: What happens
Weekly comms sync | A A A: Every Monday, 30 min; R C R: All owners + Marketing Ops; R C R: Walk Week View for next 2 weeks: clear red flags, confirm Ops readiness, agree moves.
Monthly regional planning | A A A: Last week of the month; R C R: Regional Heads + Dean (Digital) + Field; R C R: Add next month's rows; check Month View for overload per region.
Quarterly calendar review | A A A: 2 weeks before quarter start; R C R: Head of Marketing + all owners; R C R: Lock flagship moments (launches, webinars, events) and global blackout dates.
Adding a comm | A A A: As soon as it's known; R C R: Row owner; R C R: Add a row with at least Region, Channel, Segment, Launch Date, Owner, Status = Planned.
Ops request | A A A: No later than 'Brief Due By'; R C R: Row owner -> Marketing Ops; R C R: Set 'Ops Involved? = Yes', raise a ticket, paste the ticket # in the row.
Content lock | A A A: Content-lock days before launch (see Rules); R C R: Row owner + Approver; R C R: After lock, changes need Head of Marketing OK and go in the Change Log.
Customer comms heads-up | A A A: 5 business days before send; R C R: Row owner -> Customer Success; R C R: CS informed of anything reaching customers so CSMs aren't surprised.

## Rules & Guardrails
Rules & Guardrails
Yellow cells are settings — change them and every check in the calendar updates.
Max touches per segment, per region, per week |  | 2 | Proposed default. Drives the 'Frequency Flag' column. Agree the final number with the regional Heads of Marketing.
Content lock (business days before launch) |  | 5 | Proposed default. After this point, changes need Head of Marketing sign-off (log them in the Change Log).
At-risk window (days before launch) |  | 7 | Proposed default. A comm that is not fully ready inside this window is marked 'At Risk'.
Channels — group & brief lead time |  |  |  | Blackout / sensitive dates
Channel | Channel Group | Brief Lead Time (business days) | Typical Owning Team | Date | Region | Reason
Webinar | Webinar | 30 | Field Marketing | 2026-11-26 | AMER | US Thanksgiving
Email - Webinar Invite / Reminder | Email | 10 | Digital | 2026-11-27 | AMER | Black Friday - inbox saturation
Email - Newsletter | Email | 10 | Digital | 2026-12-24 | Global | Christmas Eve
Email - Campaign / Nurture | Email | 10 | Digital | 2026-12-25 | Global | Christmas Day
Email - Customer Notice | Email | 15 | Customer Success | 2026-12-26 | EMEA | Boxing Day
Social - LinkedIn | Social | 3 | Digital | 2026-12-31 | Global | New Year's Eve
Social - X | Social | 3 | Digital | 2027-01-01 | Global | New Year's Day
Social - Other | Social | 3 | Digital | 2027-02-17 | APAC | Lunar New Year
Event - In-person | Event | 40 | Field Marketing | 2027-02-18 | APAC | Lunar New Year
Event - Virtual | Event | 25 | Field Marketing
Blog / Website | Web | 5 | Content
Press Release / PR | PR | 15 | Comms / PR
In-app / Product Message | In-app | 10 | Product Marketing
Customer Community | Community | 5 | Customer Success
Paid Media | Paid | 10 | Digital
Partner Comms | Partner | 10 | Regional Marketing
Lead times are proposed defaults (blue = editable) — confirm with Marketing Ops.
Add each region's public holidays, quiet periods, earnings dates, etc.

## Change Log
Change Log
Log any change to a comm after content lock, or any date move that affects another region/team.
Date | Comm ID | What Changed | Old Value | New Value | Reason | Changed By | Approved By | Teams Notified?
2026-10-08 | AM-002 | Launch date | 13 Oct | 16 Oct (proposed) | Clashes with AM-001 to same segment | Customer Success | Head of Mkt AMER | No

## Dropdowns
Region | Audience Type | Team | Owner | Content Status | Yes / No | Overall Status | Time Zone | Frequency | Language | Region Filter
AMER | Customer | Digital | Head of Marketing (Global) | Not started | Yes | Planned | ET | One-off | EN | All
EMEA | Prospect | Field Marketing | Head of Mkt AMER | Drafting | No | In production | CT | Daily | FR | AMER
APAC | Customer + Prospect | Marketing Ops | Head of Mkt EMEA | In review | N/A | Scheduled | PT | Weekly | DE | EMEA
Global | Partner | Product Marketing | APAC Marketing Lead | Approved |  | Launched | GMT/BST | Bi-weekly | ES | APAC
| Internal | Content | Dean (Digital) |  |  | On hold | CET | Monthly | IT | Global
|  | Comms / PR | Field Marketing |  |  | Cancelled | GST (Dubai) | Quarterly | NL
|  | Customer Success | Marketing Ops |  |  |  | IST | Sequence (multi-touch) | PT
|  | Regional Marketing | Product Marketing |  |  |  | SGT |  | JA
|  |  | Customer Success |  |  |  | JST |  | ZH
[7 empty] | AEST |  | KO
AR
Multi
Edit these lists to change the dropdown options across the workbook.